| Strategies and Actions | Resources Needed | Completion Date | Expected Outcome |
| --- | --- | --- | --- |
| - Develop 16 program of study (POS) templates in conjunction with the career center | POS examples High school course listing Career center course listing List of extra-curricular activities and clubs Administrative and guidance support | 3.1.13 | 16 quality POS templates which include current information for all components as defined by state and national models |
| - Develop Personal Plan of Study (PPOS) template | PPOS examples Administrative and guidance input and approval | 4.1.13 | Personal Plan of Study Template that includes all required components as defined by state and national models |
| - Develop PPOS implementation process for grades 8 -12 which addresses student outcomes, adult actions, and time table of activities | Administrative input and support School and guidance calendars Newsletters, announcements, faculty meeting time Examples from other schools | 5.1.13 | Well defined implantation plan with specific steps, time table, and methods to educate all audiences ready to be implemented during the next school year. |
| - Students use Missouri Connections (MC) to take assessments and expand knowledge of career options and readiness skills | Computer lab time Access to MC Supporting lesson plans and curriculum | 5.1.13 | Student MC log-ins and portfolio Grade-level specific activities and results for assessment and career options and planning information |
| Strategies and Actions | Resources Needed | Completion Date | Expected Outcome |
| - Integrate career awareness information and activities into all classes | Administrative support and leadership Time with faculty Career education resources Guidance GLEs | 5.1.13 | Defined teacher outcomes Career information resource lists Documentation of lesson plans which include 2 career activities per class per quarter |
| - Communicate plan | The plan and materials Newsletters, staff meetings, email, letters home, board presentation, Career & Educational Planning Guide | 5.1.13 | Administration, counselors, faculty, board members, parents, and students have a clear understanding of the PPOS rationale, expected benefits, process, and results |